## Sheet1
Class | Fields | Methods | Data Sets | Weight | Person on Task | Completion
Name | 3 | 1 | 0 | 5 | Alex | Done
Adress | 5 | 1 | 0 | 7 | Alex | Done
User/ Account Type | 7 | 0 | 0 | 7 | Alex | Done
Admin/Account Status | 0 | 1 | 0 | 2 | Alex | Done
Login | 2 | 3 | 0 | 8 | Alex | Done
Home | 1 | 4 | 0 | 9 | Alex | Done
Cart | 4 | 3 | 1 | 15 | Jon | In Progress
Search(Interface) | 0 | 2 | 0 | 4 | Vinny | Done
Product | 6 | 1 | 0 | 8 | Alex | Done
Order/ Date and Time | 6 | 6 | 1 | 23 | Vinny | Done
Order History | 1 | 2 | 1 | 10 | Vinny | Done
Order Status | 3 | 0 | 0 | 3 | Vinny | Done
Account Info | 2 | 4 | 1 | 15 | Jon | In Progress
Database / financials | 1 | 1 | 2 | 17 | Vinny | null
| 1 Point | 2 Points | 5 Points | 133
PANE (5pnts EACH PANE)
Login |  |  |  | 5 | Alex | Done
Register |  |  |  | 5 | Alex | Done
Reset Password/Forgot Email |  |  |  | 5 | Alex | Done
home |  |  |  | 10 | jon | Done
cart/checkout |  |  |  | 10 | jon | Done
display |  |  |  | 10 | Alex | Done
information/invoice |  |  |  | 10 | Vinny | Done
financials |  |  |  | 10