## Burndown
Scrapped | 1 | Weeks | 0 | 1 | 2 | 3 | 4
In Progress | 0 | Actual Burndown | 37 | 32 | 20 | 4 | 2
Done | 7 | Ideal Burndown | 37 | 29.6 | 22.2 | 14.8 | 7.4
Feature | Priority | Estimated Days | Status | Week 1 | Week 2 | Week 3 | Week 4
Users (Not View, Edit, Add) | 1 | 2 | Done | 2 | 0 | 0 | 0
Login | 2 | 5 | Done | 1 | 4 | 0 | 0
Databases | 2 | 7 | Done | 0 | 3 | 4 | 0
Home/Shop/Cart/Checkout/Invoice | 2 | 10 | Done | 0 | 5 | 5 | 0
Products (Not View, Edit, Add) | 2 | 2 | Done | 2 | 0 | 0 | 0
Admin Home/Edit Users & Products | 3 | 4 | Done | 0 | 0 | 4 | 0
Tests | 4 | 5 | Done | 0 | 0 | 3 | 2
Product Sales/Product Clearance | 5 | 2 | Scrapped | 0 | 0 | 0 | 0