## Sheet1
Class | Fields(1 point) | Methods(2 points) | Data Sets(2 points) | Weight | Person on Task | Completion
invoice.fxml. (fx = 10 points) | - | - | - | 10 | Vinny | Done
forgotpassword.fxml (fx = 10 points) | - | - | - | 10 | Alex | Done
forgotusername.fxml (fx = 10 points) | - | - | - | 10 | Alex | Done
login.fxml (fx = 10 points) | - | - | - | 10 | Alex | Done
register.fxml (fx = 10 points) | - | - | - | 10 | Alex | Done
addproduct.fxml (fx = 10 points) | - | - | - | 10 | Vinny | Done
editproduct.fxml (fx = 10 points) | - | - | - | 10 | Vinny | Done
financialhistory.fxml (fx = 10 points) | - | - | - | 10 | Vinny | Done
viewproduct.fxml (fx = 10 points) | - | - | - | 10 | Vinny | Done
adduser.fxml | - | - | - | 10 | Jon | In Progress
adminpanel.fxml | - | - | - | 10 | Jon | In Progress
home.fxml | - | - | - | 10 | Jon | In Progress
edituser.fxml | - | - | - | 10 | Jon | In Progress
invoicehistory.fxml | - | - | - | 10 | Jon | In Progress
AccountHelper | 4 | 7 | 0 | 18 | Alex | Done
FileHelper | 5 | 10 | 0 | 25 | Vinny | Done
ProductHelper | 0 | 2 | 0 | 4 | Vinny | Done
AccountStatus | 2 | 0 | 0 | 2 | Alex | Done
AccountType | 2 | 0 | 0 | 2 | Alex | Done
Address | 4 | 3 | 0 | 10 | Alex | Done
Cart | 3 | 9 | 1 | 23 | Jon | In Progress
Name | 2 | 4 | 0 | 10 | Alex | Done
User | 12 | 23 | 1 | 60 | Alex | Done
InvoiceDatabase | 2 | 7 | 1 | 18 | Vinny | Done
OrderDatabase | 2 | 8 | 1 | 20 | Vinny | Done
ProductDatabase | 2 | 8 | 1 | 20 | Vinny | Done
UserDatabase | 2 | 11 | 1 | 26 | Vinny | Done
LoginAndRegister | 1 | 5 | 0 | 11 | Alex | Done
LoginStatus | 5 | 0 | 0 | 5 | Alex | Done
RegisterStatus | 8 | 0 | 0 | 8 | Alex | Done
ResetStatus | 6 | 0 | 0 | 6 | Alex | Done
Invoice | 3 | 4 | 0 | 11 | Vinny | Done
InvoiceTable | 5 | 6 | 0 | 17 | Vinny | Done
Order | 7 | 11 | 1 | 31 | Vinny | Done
OrderStatus | 4 | 0 | 0 | 4 | Vinny | Done
AddOrEditProduct | 1 | 3 | 0 | 7 | Vinny | Done
AddProductStatus | 5 | 0 | 0 | 5 | Vinny | Done
EditProductStatus | 5 | 0 | 0 | 5 | Vinny | Done
Product | 9 | 18 | 0 | 45 | Alex | Done
ProductStatus | 4 | 0 | 0 | 4 | Alex | Done
Financials | 2 | 6 | 0 | 14 | Vinny | Done
ShoppingCart | 8 | 12 | 0 | 32 | Alex | Done
Use Case Diagram (10 points) | - | - | - | 10 | Jon | Done
First UML Diagram (5 points) | - | - | - | 5 | Alex | Done
Final UNL Diagram (15 points) | - | - | - | 15 | Jon | In Progress
Finding Product Images (15 points) | - | - | - | 15 | Jon
|  |  | Total Points: | 578
|  |  |  | 18 | : Alex
|  |  |  | 19 | : Vinny
|  |  |  | 9 | : Jon