## Sheet1
Class/Assignment | Fields(1 point) | Methods(2 points) | Data Sets(2 points) | Weight | Person on Task | Completion | DAY COMPLETED
invoice.fxml. (fx = 10 points) | - | - | - | 10 | Vinny | Done | 2020-02-20
forgotpassword.fxml (fx = 10 points) | - | - | - | 10 | Alex | Done | 2020-02-15
forgotusername.fxml (fx = 10 points) | - | - | - | 10 | Alex | Done | 2020-02-15
login.fxml (fx = 10 points) | - | - | - | 10 | Alex | Done | 2020-02-15
register.fxml (fx = 10 points) | - | - | - | 10 | Alex | Done | 2020-02-15
addproduct.fxml (fx = 10 points) | - | - | - | 10 | Vinny | Done | 2020-02-21
editproduct.fxml (fx = 10 points) | - | - | - | 10 | Vinny | Done | 2020-02-21
financialhistory.fxml (fx = 10 points) | - | - | - | 10 | Vinny | Done | 2020-02-22
viewproduct.fxml (fx = 10 points) | - | - | - | 10 | Vinny | Done | 2020-02-21
adduser.fxml | - | - | - | 10 | Jon | Done | 2020-02-22
adminpanel.fxml | - | - | - | 10 | Jon | Done | 2020-02-22
home.fxml | - | - | - | 10 | Jon | Done | 2020-02-22
edituser.fxml | - | - | - | 10 | Jon | Done | 2020-02-23
invoicehistory.fxml | - | - | - | 10 | Jon | Done | 2020-02-21
AccountHelper | 4 | 7 | 0 | 18 | Alex | Done | 2020-02-15
FileHelper | 5 | 10 | 0 | 25 | Vinny | Done | 2020-02-22
ProductHelper | 0 | 2 | 0 | 4 | Vinny | Done | 2020-02-21
AccountStatus | 2 | 0 | 0 | 2 | Alex | Done | 2020-02-16
AccountType | 2 | 0 | 0 | 2 | Alex | Done | 2020-02-16
Address | 4 | 3 | 0 | 10 | Alex | Done | 2020-02-15
Cart | 3 | 9 | 1 | 23 | Jon | Done | 2020-02-21
Name | 2 | 4 | 0 | 10 | Alex | Done | 2020-02-14
User | 12 | 23 | 1 | 60 | Alex | Done | 2020-02-16
InvoiceDatabase | 2 | 7 | 1 | 18 | Vinny | Done | 2020-02-20
OrderDatabase | 2 | 8 | 1 | 20 | Vinny | Done | 2020-02-20
ProductDatabase | 2 | 8 | 1 | 20 | Vinny | Done | 2020-02-20
UserDatabase | 2 | 11 | 1 | 26 | Vinny | Done | 2020-02-20
LoginAndRegister | 1 | 5 | 0 | 11 | Alex | Done | 2020-02-21
LoginStatus | 5 | 0 | 0 | 5 | Alex | Done | 2020-02-15
RegisterStatus | 8 | 0 | 0 | 8 | Alex | Done | 2020-02-15
ResetStatus | 6 | 0 | 0 | 6 | Alex | Done | 2020-02-15
Invoice | 3 | 4 | 0 | 11 | Vinny | Done | 2020-02-19
InvoiceTable | 5 | 6 | 0 | 17 | Vinny | Done | 2020-02-21
Order | 7 | 11 | 1 | 31 | Vinny | Done | 2020-02-20
OrderStatus | 4 | 0 | 0 | 4 | Vinny | Done | 2020-02-16
AddOrEditProduct | 1 | 3 | 0 | 7 | Vinny | Done | 2020-02-21
AddProductStatus | 5 | 0 | 0 | 5 | Vinny | Done | 2020-02-21
EditProductStatus | 5 | 0 | 0 | 5 | Vinny | Done | 2020-02-21
Product | 9 | 18 | 0 | 45 | Alex | Done | 2020-02-20
ProductStatus | 4 | 0 | 0 | 4 | Alex | Done | 2020-02-20
Financials | 2 | 6 | 0 | 14 | Vinny | Done | 2020-02-21
ShoppingCart | 8 | 12 | 0 | 32 | Alex | Done | 2020-02-16
Use Case Diagram (10 points) | - | - | - | 10 | Jon | Done | 2020-02-13
First UML Diagram (5 points) | - | - | - | 5 | Alex | Done | 2020-02-13
Final UNL Diagram (15 points) | - | - | - | 15 | Jon | Done | 2020-02-23
|  |  | Total Points: | 563